## checklist
CHECKLIST |  | BOOKSHOP WEBSITE
Project Start | 2018-12-11 |  |  |  |  | Project End | 2x/12/2018
TASK | OWNER | PRIORITY | START | END | % COMPLETE | DONE | NOTES
Requirements | [5 empty] | 0
Introduction | Nguyễn Huỳnh Bảo Hân | MEDIUM | 2018-12-11 | 2018-12-12 | 100% | 0 | Deliver the product according to the intended time and try to correct it when requested by the customer.
Overall Description | Nguyễnn Lê Thanh Bách | HIGH | 2018-12-11 | 2018-12-12 | 100% | 0 | Deliver the product according to the intended time and try to correct it when requested by the customer.
External Interface Requirements | Phạm Anh Tuấn | MEDIUM | 2018-12-12 | 2018-12-14 | 100% | 0 | Deliver the product according to the intended time and try to correct it when requested by the customer.
System Features | Nguyễn Lê Thanh Bách | HIGH | 2018-12-12 | 2018-12-13 | 100% | 0 | Deliver the product according to the intended time and try to correct it when requested by the customer.
Other nonfunctional requirements and other requirements | Nguyễn Lê Thanh Bách | MEDIUM | 2018-12-18 | 2018-12-19 | 100% | 0 | Deliver the product according to the intended time and try to correct it when requested by the customer.
Review and call to fix | Phạm Anh Tuấn | MEDIUM | 2018-12-20 | 2018-12-21 | 100% | 0 | Deliver the product according to the intended time and try to correct it when requested by the customer.
Design | [5 empty] | 0
Layout Design | Phạm Anh Tuấn | HIGH | 2018-12-16 | 2018-12-18 | 100% | 0 | The interface exactly matches the requirements set. Some parts need correcting
UML Diagram | Nguyễn Quốc Cường | HIGH | 2018-12-16 | 2018-12-19 | 100% | 0 | The interface exactly matches the requirements set. Some parts need correcting
Code - Front end | [5 empty] | 0
Registration | Nguyễn Thiện Chí | HIGH | 2018-12-18 | 2018-12-20 | 100% | 0 | Code clean, easy to understand but there are some missing functions.
Home screen | Nguyễn Huỳnh Bảo Hân | MEDIUM | 2018-12-18 | 2018-12-20 | 100% | 0 | Code clean, easy to understand but there are some missing functions.
Detail screen | Nguyễn Thiện Chí | HIGH | 2018-12-19 | 2018-12-21 | 100% | 0 | Code clean, easy to understand but there are some missing functions.
| Nguyễn Lê Thanh Bách | HIGH | 2018-12-19 | 2018-12-21 | 100% | 0 | Code clean, easy to understand but there are some missing functions.
| Nguyễn Huỳnh Bảo Hân | HIGH | 2018-12-19 | 2018-12-21 | 100% | 0 | Code clean, easy to understand but there are some missing functions.
| Nguyễn Quốc Cường | HIGH | 2018-12-19 | 2018-12-21 | 100% | 0 | Code clean, easy to understand but there are some missing functions.
| Phạm Anh Tuấn | HIGH | 2018-12-19 | 2018-12-21 | 100% | 0 | Code clean, easy to understand but there are some missing functions.
Create database + insert values | Nguyễn Quốc Cường | HIGH | 2018-12-20 | 2018-12-21 | 100% | 0 | Code clean, easy to understand but there are some missing functions.
| Phạm Anh Tuấn | HIGH | 2018-12-20 | 2018-12-21 | 100% | 0 | Code clean, easy to understand but there are some missing functions.
| Ngueyẽn Thiện Chí | HIGH | 2018-12-20 | 2018-12-21 | 100% | 0 | Code clean, easy to understand but there are some missing functions.
| Nguyễn Huỳnh Bảo Hân | HIGH | 2018-12-20 | 21/12/208 | 100% | 0 | Code clean, easy to understand but there are some missing functions.
Check + Complete database | Nguyễn Lê Thanh Bách | HIGH | 2018-12-22 | 2018-12-21 | 100% | 0 | Code clean, easy to understand but there are some missing functions.
Code - Back end | [5 empty] | 0 | Code clean, easy to understand but there are some missing functions.
Login and registration | Nguyễn Lê Thanh Bách | HIGH | 2018-12-21 | 2018-12-22 | 100% | 0 | Relatively complete and detailed database. deliver the product on time but there are some functions of the web that are incomplete
| Nguyễn Thiện Chí | HIGH | 2018-12-21 | 2018-12-22 | 100% |  | Relatively complete and detailed database. deliver the product on time but there are some functions of the web that are incomplete
Add products | Nguyễn Thiện Chí | HIGH | 2018-12-20 | 2018-12-23 | 100% | 0 | Relatively complete and detailed database. deliver the product on time but there are some functions of the web that are incomplete
Delete products | Nguyễn Quốc Cường | HIGH | 2018-12-20 | 2018-12-23 | 100% | 0 | Relatively complete and detailed database. deliver the product on time but there are some functions of the web that are incomplete
Edit Products | Phạm Anh Tuấn | HIGH | 2018-12-20 | 2018-12-23 | 100% | 0 | Relatively complete and detailed database. deliver the product on time but there are some functions of the web that are incomplete
Add to cart | Nguyễn Huỳnh Bảo Hân | HIGH | 2018-12-20 | 2018-12-23 | 100% | 0 | Relatively complete and detailed database. deliver the product on time but there are some functions of the web that are incomplete
Search products | Nguyễn Thiện Chí | HIGH | 2018-12-23 | 2018-12-26 | 100% |  | Relatively complete and detailed database. deliver the product on time but there are some functions of the web that are incomplete
| Nguyễn Lê Thanh Bách | HIGH | 2018-12-23 | 2018-12-26 | 100% |  | Relatively complete and detailed database. deliver the product on time but there are some functions of the web that are incomplete
Unit Testing | [5 empty] | 0
Re-check customer requirements | All team | HIGH | 2018-12-24 | 2018-12-27 | 100% | 0
Check requirements | All team | MEDIUM | 2018-12-24 | 2018-12-27 | 100% | 0
Check front end | All team | MEDIUM | 2018-12-24 | 2018-12-27 | 90% | 0
Check back end | All team | MEDIUM | 2018-12-24 | 2018-12-27 | 90% | 0